## Sheet1
Risk Identification | Affects | Mitigation | Analysis | Monitoring
Lack of communication | Conflicts; missed deadlines; low morale | Weekly meetings; ensure we all communicate regularly | Work from other modules meaning not enough time to focus on this project (medium) | Check everyone has seen any developments; regular meetings; ensure if someone isn't present, we catch up with them
Poor tool and language choice | Deadlines missed; low quality work; stress | Go through all possible options and choose the tools and language that everyone agrees would be best unanmously; help those with less experience | Poor communication (high); inexperience with language/tool (medium) | Review progress frequently; help those struggling by giving them 'easier' or fewer tasks
Incorrect time allocation for tasks | Deadlines missed; rushed work; complacency | Set reasonable deadlines everyone is happy with; update deadlines on the go when necessary | Poor communication (high); bad time management (high); poor planning (medium) | Check development regularly; raise and respond to any concerns over the deadlines; distribute workload effectively
Game doesn't work on certain machines | Limits usability; doesn't meet client requirements | Develop product to be used on multiple machines; test frequently on different devices | Poor planning (high); poor communication with customer (medium) | Frequent testing on different machines; communicate with client
Workload mismanagement | Conflicts; missed deadlines; low morale | Make sure everyone is happy with their roles and workload; distribute work responsibly | Poor communication (high); poor planning (high); unreasonable expectations (medium) | Frequent updates on task progress; share workload for larger tasks; communicate
Poor planning | Missed deadlines; unhappy customer; low quality work | PERT charts to track progress; weekly meetings to discuss progress; | Poor understanding of client expecations (medium); poor communication with team and client (high) | Check client specification regularly and compare to developemtn; update/create PERTs regularly; team meetings weekly
Conflicts | Low morale; deadlines missed; poor work | Resolve any conflicts; frequent communication and meetings; teamwork | Poor communication (high); uneven workloads (medium); | Raise and address any issues and problems when they arise; check eveyrone is happy during the team meetings; team building
Missed deadlines | Low morale; unhappy client; development falling behind schedule | Review progress frequently; raise any concerns with meeting deadlines; set achievable deadlines | Poor communication (medium); bad planning (medium); unrealistic workloads and deadlines (high); other work (low) | Weekly team meetings and daily communication to track progress; allow slack time between tasks
Illness | Missing uni, meetings; unable to work; Fall behind | Share workload of the unwell member; flexibility in deadlines and meetings | Poor communication (medium); luck (high); cold weather (high) | Communincate when unwell and its affect on performance; change meetings and workload to accommodate
Traffic, trains and buses | Missing uni; missing meetings; lowers morale; lateness | Plan ahead by checking disruptions before leaving; communicate with team | Poor travel planning (high); misfortune (medium) | Inform of any disruptions to team; alert team when you will be late/ miss events
Other coursework | Less time for this project; fall behind schedule; stress | Alert teammates if other coursework is time consuming; share workload; be flexible with schedule | Poor communication (medium); time management (high); stress from worklaod (low) | Inform teammates of any struggles or priorities; allow flexibility for catchup time; keep up with meetings/decisions