## PERT Main
Task | Description | Duration | Earliest Start Date | Earliest Finish Date | Latest Start Date | Latest Finish Date | Predecessor(s) | Critical Path | Ontime Completion? | Setbacks and Reasons
A | Form team | 3 | Day 0 | Day 3 | Day 0 | Day 3 | None | Yes | Yes, day 3
B | Assign roles | 3 | Day 3 | Day 6 | Day 3 | Day 6 | A | Yes | Yes, day 6
C | Decide version control and communication methods | 3 | Day 3 | Day 6 | Day 3 | Day 6 | A | Yes | Yes, day 6
D | Requirement analysis | 3 | Day 6 | Day 9 | Day 6 | Day 9 | B,C | Yes | Yes, day 9
E | Rule interpretation | 3 | Day 9 | Day 12 | Day 9 | Day 12 | B,D | Yes | Yes, day 12 | Misinterpretation and ambiguity in the specification led to questions being raised to Mr Raffles for clarity
F | Design research and creation | 3 | Day 6 | Day 9 | Day 12 | Day 15 | B | No | Yes, day 12
G | Finalise design | 3 | Day 9 | Day 12 | Day 15 | Day 18 | F | No | Yes, day 15 | Took longer than planned due to illness and misreading the brief. At first we thought we designed our own board, but then we realised there was an excel sheet stating the different tile properties
H | AI difficulty and behaviours | 3 | Day 9 | Day 12 | Day 15 | Day 18 | D | No | Yes, day 16 | Later start for this as we were focussed on other aspects of the game. This was not a priority at the time and also wasn't part of the critical path so we had some slack time.
I | Programming language | 3 | Day 9 | Day 12 | Day 9 | Day 12 | C,D | Yes | Yes, day 12
J | Programming development | 36 | Day 12 | Day 48 | Day 12 | Day 48 | D,E,I | Yes
K | Core game coding | 24 | Day 12 | Day 36 | Day 18 | Day 42 | D,E,I | No
L | GUI coding | 24 | Day 12 | Day 36 | Day 18 | Day 42 | D,G,I | No
M | AI coding | 24 | Day 12 | Day 36 | Day 18 | Day 42 | D,E,H,I | No
N | Testing | 36 | Day 12 | Day 48 | Day 12 | Day 48 | D,E,I | Yes
O | Bug fixing | 6 | Day 32 | Day 38 | Day 42 | Day 48 | K,L,M | No
P | Record meetings and sprint, update PERT and Risks | 42 | Day 3 | Day 45 | Day 5 | Day 47 | B | No
Q | Collect all documents from sprints and team meetings etc. | 1 | Day 45 | Day 46 | Day 47 | Day 48 | P | No
R | Group report | 6 | Day 48 | Day 54 | Day 48 | Day 54 | J,N,O,Q | Yes
S | Combine all documents and deliverables | 3 | Day 54 | Day 57 | Day 54 | Day 57 | J,N,Q, R | Yes
T | Check and finalise submission | 3 | Day 57 | Day 60 | Day 57 | Day 60 | S | Yes
U | Submission | 0 | Day 60 | Day 60 | Day 60 | Day 60 | T | Yes

## Pert Additional
Task ID | Overruling Task | Description | Duration | Earliest Start Date | Earliest Finish Date | Latest Start Date | Latest Finish Date | Predecessor(s) | Critical Path | Ontime Completion? | Setbacks and Reasons
1 | J, K | Implementing the rules | 6 | Day 12 | Day 18 | Day 21 | Day 27 | N/a | No
2 | J, K | Implementing the basic actions, such as moving around the board and dice rolling | 3 | Day 12 | Day 15 | Day 12 | Day 15 | N/a | Yes
3 | J, K | Ability to purchase a property and its houses / hotel | 3 | Day 15 | Day 18 | Day 15 | Day 18 | 2, 15 | Yes
4 | J, K | Paying rent | 3 | Day 18 | Day 21 | Day 24 | Day 27 | 3, 15 | No
5 | J, K | Mortgaging a property | 3 | Day 18 | Day 21 | Day 24 | Day 27 | 3 | No
6 | J, K | Game modes | 12 | Day 12 | Day 24 | Day 18 | Day 30 | N/a | No
7 | J, K | Coding time limit | 12 | Day 24 | Day 36 | Day 30 | Day 42 | 6 | No
8 | J, K | Auction | 6 | Day 21 | Day 27 | Day 21 | Day 27 | 3, 15 | Yes
9 | J, L | Players position on board being visible | 6 | Day 15 | Day 21 | Day 36 | Day 42 | 2 | No
10 | J, L | Players money being visible | 6 | Day 12 | Day 18 | Day 36 | Day 42 | N/a | No
11 | J, L | Implementation of visible actions | 12 | Day 15 | Day 27 | Day 32 | Day 42 | 2 | No
12 | J, L | UI for starting the game | 6 | Day 12 | Day 18 | Day 36 | Day 42 | N/a | No
13 | J, L | Zoom in and out feature | 12 | Day 24 | Day 36 | Day 30 | Day 42 | 14 | No
14 | J, L | Implementing board design | 12 | Day 12 | Day 24 | Day 18 | Day 30 | N/a | No
15 | J, L | Uploading game data | 3 | Day 12 | Day 15 | Day 12 | Day 15 | N/a | Yes
16 | J, M | Difficulty levels | 6 | Day 33 | Day 42 | Day 33 | Day 42 | 16 | Yes
17 | J, M | Behaviour | 6 | Day 27 | Day 33 | Day 27 | Day 33 | 1, 2, 3, 4, 5, 8 | Yes