## PERT Main
Task | Description | Duration | Earliest Start Date | Earliest Finish Date | Latest Start Date | Latest Finish Date | Predecessor(s) | Critical Path | Ontime Completion? | Setbacks and Reasons
A | Form team | 3 | Day 0 | Day 3 | Day 0 | Day 3 | None | Yes | Yes, day 3
B | Assign roles | 3 | Day 3 | Day 6 | Day 3 | Day 6 | A | Yes | Yes, day 6
C | Decide version control and communication methods | 3 | Day 3 | Day 6 | Day 3 | Day 6 | A | Yes | Yes, day 6
D | Requirement analysis | 3 | Day 6 | Day 9 | Day 6 | Day 9 | B,C | Yes | Yes, day 9
E | Rule interpretation | 3 | Day 9 | Day 12 | Day 9 | Day 12 | B,D | Yes | Yes, day 12 | Misinterpretation and ambiguity in the specification led to questions being raised to Mr Raffles for clarity
F | Design research and creation | 3 | Day 6 | Day 9 | Day 12 | Day 15 | B | No | Yes, day 12
G | Finalise design | 3 | Day 9 | Day 12 | Day 15 | Day 18 | F | No | Yes, day 15 | Took longer than planned due to illness and misreading the brief. At first we thought we designed our own board, but then we realised there was an excel sheet stating the different tile properties
H | AI difficulty and behaviours | 3 | Day 9 | Day 12 | Day 15 | Day 18 | D | No | Yes, day 16 | Later start for this as we were focussed on other aspects of the game. This was not a priority at the time and also wasn't part of the critical path so we had some slack time.
I | Programming language | 3 | Day 9 | Day 12 | Day 9 | Day 12 | C,D | Yes | Yes, day 12
J | Programming development | 36 | Day 12 | Day 48 | Day 12 | Day 48 | D,E,I | Yes
K | Core game coding | 24 | Day 12 | Day 36 | Day 18 | Day 42 | D,E,I | No | Yes, day 42
L | GUI coding | 24 | Day 12 | Day 36 | Day 18 | Day 42 | D,G,I | No | Yes, day 36
M | AI coding | 24 | Day 12 | Day 36 | Day 18 | Day 42 | D,E,H,I | No | Yes, day 42
N | Testing | 36 | Day 12 | Day 48 | Day 12 | Day 48 | D,E,I | Yes | Yes, day 48
O | Bug fixing | 6 | Day 32 | Day 38 | Day 42 | Day 48 | K,L,M | No | No, day 52 | Ongoing process as bugs continue to crop up as development and testing continues
P | Record meetings and sprint, update PERT and Risks | 42 | Day 3 | Day 45 | Day 5 | Day 47 | B | No | No, day 51 | Bug fixing took longer than expected which meant we were delayed with document updates
Q | Collect all documents from sprints and team meetings etc. | 1 | Day 45 | Day 46 | Day 47 | Day 48 | P | No | No, day 52 | Due to delay in P
R | Group report | 6 | Day 48 | Day 54 | Day 48 | Day 54 | J,N,O,Q | Yes | No, day 58 | Delay in previous tasks, as well as other modules courseworks taking up our time
S | Combine all documents and deliverables | 3 | Day 54 | Day 57 | Day 54 | Day 57 | J,N,Q, R | Yes | No, day 61 | `
T | Check and finalise submission | 3 | Day 57 | Day 60 | Day 57 | Day 60 | S | Yes | No, day 62 | Delayed but was a lot quicker than expected due to keeping everything organised
U | Submission | 0 | Day 60 | Day 60 | Day 60 | Day 60 | T | Yes | No, day 63 | Took an extra day for it, but still within the allowed timeframe for submission

## Pert Additional
Task ID | Overruling Task | Description | Duration | Earliest Start Date | Earliest Finish Date | Latest Start Date | Latest Finish Date | Predecessor(s) | Critical Path | Ontime Completion? | Setbacks and Reasons
1 | J, K | Implementing the rules | 6 | Day 12 | Day 18 | Day 21 | Day 27 | N/a | No | Yes, day 18
2 | J, K | Implementing the basic actions, such as moving around the board and dice rolling | 3 | Day 12 | Day 15 | Day 12 | Day 15 | N/a | Yes | Yes, day 15 | A few bugs cropped up but they were handled accordingly
3 | J, K | Ability to purchase a property and its houses / hotel | 3 | Day 15 | Day 18 | Day 15 | Day 18 | 2, 15 | Yes | Yes, day 18
4 | J, K | Paying rent | 3 | Day 18 | Day 21 | Day 24 | Day 27 | 3, 15 | No | Yes, day 25
5 | J, K | Mortgaging a property | 3 | Day 18 | Day 21 | Day 24 | Day 27 | 3 | No | Yes, day 23
6 | J, K | Game modes | 12 | Day 12 | Day 24 | Day 18 | Day 30 | N/a | No | Yes, day 28
7 | J, K | Coding time limit | 12 | Day 24 | Day 36 | Day 30 | Day 42 | 6 | No | Yes, day 42 | Implemented correctly and ontime, but was changed later onn to include more time options and customizability
8 | J, K | Auction | 6 | Day 21 | Day 27 | Day 21 | Day 27 | 3, 15 | Yes | Yes, day 27
9 | J, L | Players position on board being visible | 6 | Day 15 | Day 21 | Day 36 | Day 42 | 2 | No | Yes, day 21
10 | J, L | Players money being visible | 6 | Day 12 | Day 18 | Day 36 | Day 42 | N/a | No | Yes, day 36
11 | J, L | Implementation of visible actions | 12 | Day 15 | Day 27 | Day 32 | Day 42 | 2 | No | Yes, day 28
12 | J, L | UI for starting the game | 6 | Day 12 | Day 18 | Day 36 | Day 42 | N/a | No | Yes, day 33
13 | J, L | Zoom in and out feature | 12 | Day 24 | Day 36 | Day 30 | Day 42 | 14 | No | Yes, day 36 | Created a few bugs but were easily fixable
14 | J, L | Implementing board design | 12 | Day 12 | Day 24 | Day 18 | Day 30 | N/a | No | Yes, day 24 | Constantly updated but initially was completed on time
15 | J, L | Uploading game data | 3 | Day 12 | Day 15 | Day 12 | Day 15 | N/a | Yes | Yes, day 15
16 | J, M | Difficulty levels | 6 | Day 33 | Day 42 | Day 33 | Day 42 | 17 | Yes | Yes, day 42
17 | J, M | Behaviour | 6 | Day 27 | Day 33 | Day 27 | Day 33 | 1, 2, 3, 4, 5, 8 | Yes | Yes, day 33